FAO National Forest Programme Facility

Ridge to Reef Watershed Project

Forestry Department

Senior Managers’ Workshop

to Develop a Framework for

the Preparation of the 2006-2010

National Forest Management

and Conservation Plan

##### November 3 – 4, 2004

- Prepared for the

- Government of Jamaica’s Forestry Department

- FAO National Forest Programme Facility

- Government of Jamaica’s National Environment and Planning Agency

- and the

- United States Agency for International Development

## Table of Contents

## General	5

## Welcome, Introductions and Opening Comments	5

## Session 1 - Preparation and Reflection on a Balance Sheet	7

## Identifying and Prioritization of Issues	8

## Strategic Directions for a New Forest Plan	11

## Action Planning for a New Forest Plan	12

## Victory Circle		22

## Schedule or Calendar for Preparation of 2006-2010 National Forest Management and Conservation Plan	23

## Project Steering Committee	23

## Implementation Wedge	23

## Tables

## Table 1	One Word that Best Describe Self	6

## Table 2	Conference Expectations in On Word	6

## Table 3	Worksheet 1 – Balance Sheet	7

## Table 4	Major Lessons and/or Practices to be Carried Forward	9

## Table 5	Key Issues to be Included in a New Forest Plan	9

## Table 6	Key Organizations and their Role in a New Forest Plan	10

## Table 7	Effective Incentive Program	13

## Table 8 	LFMCs	14

## Table 9 	Effective Organizational Structure	15

## Table 10 	Forest Management System	16

## Table 11 	Strategies to Improve Revenue Potential	17

## Table 12 	Forestry Information System	18

## Table 13 	National Forest Public Education Program	19

## Table 14 	Capacity Building Program	20

## Table 15	Comprehensive Enforcement Plan	21

## Diagrams

## Diagram 1	Victory Circle	22

## Diagram 2	Immediate Plan of Action	24

## Diagram 3	Schedule of Calendar for Preparation of 2006-2010 National Forest

## Management and Conservation Plan	25

## Appendices

## Appendix 1 	Agenda	27

## Appendix 2	Worksheet 1 – Balance Sheet	29

## Appendix 3	Worksheet 2 – Issues for Discussion	30

## Appendix 4	Worksheet 3 – Action Planning	34

## Appendix 5	List of Participants	35

## General

The Senior Management Staff of the Forestry Department (FD) participated in a Retreat at the Sans Souci Resort & Spa from November 3-5, 2004. The Retreat (Please see Appendix 1 for Agenda) involved participants in:

- Receiving presentations on the existing status of the National Forest Management and Conservation Plan, taking into consideration that the FD will undergo a modernization process, and possibly be reorganized as an Executive Agency;

- Developing a Balance Sheet that will assist the FD to determine the things that it did well in implementing the National Forest Management and Conservation Plan, and those that could be improved on;

- Establishing the Strategic Directions for the FD for a new National Forest Management and Conservation Plan for the period 2006-2010;

- Establishing an Action Plan for the FD over the period of the new National Forest Management and Conservation Plan; and

- Establishing timeline for next steps (preparation of draft plan, public consultations to present draft document, printing etc).

The Retreat is one of the activities in the Forestry Department’s programme of work funded by a grant from the FAO National Forest Programme Facility. Additional assistance was received from the USAID-funded Ridge to Reef Watershed Project which provided the services of a facilitor to guide the Retreat’s proceedings.

## Welcome, Introductions, and Opening Comments

The Conservator of Forests, Miss Marilyn Headley welcomed all participants; invited Mr. Alli Morgan to lead the group in prayers; reminded participants of the significance of the Retreat; informed everyone about the logistics; provided a short status report; and welcomed Trevor Spence, the Facilitator for the Retreat.

Trevor expressed his joy to be sharing with the Senior Management Staff of the Forestry Department in this way, and walked participants through the Agenda, and Methodology for the Retreat.

## Introductions

Participants were asked to use one word that best describe themselves or how they felt. This was done alphabetically. The words selected by participants are listed in Table 1 below:

Table 1 	One Word that Best Describe Self

| A | LL-PURPOSE |
| --- | --- |
| B | UREAUCRACY (NON) |
| C | ALM |
| D | OMINANT |
| E | NTERTAINMENT |
| F | INANCE |
| G | ENERAL (CHIEF) |
| H | APPY |
| I | NITIATIVE |
| J | OVIAL |
| K | IND (OF) |
| L | AUGHING (KOOL) |
| M | ANAGEMENT |
| N | OSTALGIC |
| O | PTIMISTIC |
| P | ERSEVERANCE |
| Q | UALITY-CENTERED |
| R | ESPONSIBLE |
| S | ENSITIVE |

Participants then used one word to describe their expectation of the Retreat. This is listed in Table 2 below:

Table 2		Conference Expectations in One Word

| HOPEFUL | CONCISE | COMMUNITY |
| --- | --- | --- |
| CLARITY | INFORMATION | INVOLVEMENT |
| ENCOURAGED | PARTICIPATION | COMMITMENT |
| MONEY | PROACTIVE | REALISTIC |
| DEVELOP | CONCENSUS | STRATEGIZE |
| MEANINGFUL | VISIBILITY | ENABLE |

## SESSION 1	Preparation and Reflection on a Balance Sheet

The first session of the Retreat followed. This was developing a Balance Sheet indicating “Things the FD has done well”, and “Things that could be improved on, or not done at all”. The activities of the FD were reviewed, and members brainstormed individually, in small groups, and in plenary to put these in the Done Well or Need Improvement columns and in some areas, indicated the reason for their assessment. Worksheet 1 (Please see Appendix 2) was used for this purpose. The outcome is listed below in Table 3:

Table 3		Worksheet 1 – Balance Sheet

| Done Well/Improved | #### Comments |
| --- | --- |
| Production of manuals and Annual and other reports |  |
| Customer service - internal and external - significantly improved |  |
| Nursery production improved – with little resources |  |
| Community involvement - willingness of staff to change |  |
| Improved accountability and transparency in financial management |  |
| Improved executive and team leadership |  |
| General staff adaptability improved |  |
| Technical forest resource information capabilities improved: - Mapping and inventory - GIS |  |
| Collaboration with NGOs, GOJ, Private Sector and Communities | Increase investment incentives |
| NFMCP – drafting process done well |  |
| Public education and awareness and communications – FD image greatly improved |  |
| Improved infrastructure (improvement at HQ more obvious) |  |
| Training opportunities increased |  |
| TFT Project – Project activities fully integrated into FD |  |
| Improvement/greater acceptance of gender equality |  |

| Need Improvement/Not Done | Comments |
| --- | --- |
| Documentation/information management - - Registry, library needs improvement - - Issues with archiving |  |
| Internal communication/motivation - Gap between senior and junior staff - Need to boost staff morale - Assessment of human resources needs to be put in place |  |
| Training (not getting value) |  |
| Monitoring, follow-up and evaluation needs boosting Identification of resources not complete |  |
| Inclusion of public in deriving benefits from forest resources - LFMC program needs to be revitalized |  |
| Protection and enforcement |  |
| Local forest management plans needed |  |
| Succession planning |  |
| Private planting program not meeting potential |  |
| Reforestation, forest management and maintenance targets not being met |  |
| Implement flexi-work time |  |
| Implementation of goals identified on schedule (NFMCP) |  |
| Recruiting of specialist forestry personnel |  |
| Research program need a boost - Funding etc. - Needs clear definition between technical and social research |  |
| Innovative funding mechanisms needed |  |
| Sustainability of external funding sources |  |

Identifying and Prioritization of Issues

A one page presentation of issues was presented and discussed. This was expected to assist the FD in determining: what are the practical actions the Department needs to undertake over the next five years to assist it in implementing the Forest Plan? Worksheet 2 (Please see Appendix 3) was used to guide participants in this activity.

Participants were placed in six groups, namely:

Group 1– Policy and Legal Framework

Group 2 – Forest Resources Information

Group 3 – Role of FD in Forestry Productive Sector

Group 4 – Community Participation and Public Education

Group 5 – Communications Program

Group 6 – Administration and HRD

They were first asked to list the three (3) major lessons and/or practices that should be carried forward from the existing Forest Plan to the new one for the area they were examining. Listed below in Table 4 are the Groups’ responses:

Table 4 	Major Lessons and/or Practices to be Carried Forward

| Group 1 – Policy and Legal Framework | - Forest protection - Income generation opportunity - Strategy for private and public investment |
| --- | --- |
| Group 2 – Forest Resources Information | - FD should continue to be the national focal point for forest resources information collection, analysis and management - Research should be “standard” component of other FD activities, eg, as part of seedling production - Assessment of commercial potential for forest reserves |
| Group 3 – Role of FD in Forestry Productive Sector | - Increased collaboration/co-operation with GOJ, NGOs, private sector, etc. - Inventory and sale of timber - Continuation of Private Planting Programme - move forward |
| Group 4 – Community Participation and Public Education | - Promotion of community–driven collaboration - Build capacity of FD staff for extension - Make forest management attractive to communities |
| Group 5 – Communications Programme | - Retention of identified target groups - Inter-agency collaboration (NEPA, MLE) - Use of popular educational techniques (formal and informal sector) |
| Group 6 – Administration and HRD | - FD training needs assessment - Tie performance management to motivation and moral building - Investment and incentive - Gender equity |

Participants were next asked to name the three (3) key new issues they believed must be included in a new Forest Plan for the area they were examining. Their responses are included in Table 5 below:

Table 5		Key Issues to be included in a New Forest Plan

| Group 1 – Policy and Legal Framework | - More efficient permit and licensing system - Legislation should cover private lands - Institutionalising collaboration with other agencies and policies |
| --- | --- |

| Group 2 – Forest Resources Information | - LFMP should include: - Assessment capabilities - Research - Assessment of commercial potential - Formation of Forest Management Plan should engage Regional FD staff and LFMC - Urban Forest Management Plan |
| --- | --- |
| Group 3 – Role of FD in Forestry Productive Sector | - Expanded incentive programme for private sector involvement - Development of a non-timber products programme - Identify and collaborate with wood users - Establishing eco-tourism and incorporate (lobby for) management of terrestrial national parks by FD |
| Group 4 – Community Participation and Public Education | - Identify resources and set out benefits to be derived so as to make them accessible - De-centralize community involvement - Increase capacity building within community |
| Group 5 – Communications Programme | - Design messages and delivery methods for adult population - Collaboration with government agencies, NGOs - sponsorship from private sector - Design evaluation methodology |
| Group 6 – Administration and HRD | - Internal incentives - Streamlining of information and documentation systems - Role of Executive Agency - Financial Management reporting - production and feedback |

Participants then named the three (3) Key Organizations and their likely role in partnering the FD in the successful implementation of this new plan. Table 6 below list the results:

Table 6		Key Organizations and their Role in a New Forest Plan

| Group 1 – Policy and Legal Framework | - Ministry of Finance - Ministry of Lands & Environment, NEPA and National Land Agency - Ministry of National Security, Ministry of Justice |
| --- | --- |
| Group 2 – Forest Resources Information | - NEPA - NWC - UDC |
| Group 3 – Role of FD in Forestry Productive Sector | - NWC - National Wood Workers Association - National Tree Growers Association - Jamaica Manufacturers Association |
| Group 4 – Community Participation and Public Education | - JAS - RADA - GOJ (Finance funding) - 4H Club(s) |
| Group 5 – Communications Program | - NEPA - Ministry of Education Youth & Culture - Mainstream Media - Private sector of Jamaica (and others) |
| Group 6 – Administration and HRD | - Ministry of Finance/Cabinet Office - Offices of the Services Commissions - Ministry of Agriculture - Private sector (bauxite companies) |

Participants were finally asked to list any other comments they had regarding their area in the Forest Plan. A summary of the comments from all groups are:

- Review of Forest Plan vis a vis goals

- Review Forest Act and amend Regulations

- Prioritisation of activities re human and financial resources needed

- Revise layout of NFMCP

- Local and national communication programme is well laid out in plan

Strategic Directions for a New Forest Plan

Using the Focus Question - What strategies need to be included in developing a new Forest Plan 2006 – 2010 - participants worked in Groups to prioritize the issues, and to identify Strategies and Activities for the new Forest Plan. The information from Worksheet 2 and the above focus question assisted in brainstorming to capture the selected priority areas

- Nine strategic directions were compiled by workshop group for action planning. The strategies are listed below in random order (i.e., they have not been assigned a specific priority):

- Establishment of an effective incentive program to cover the various needs of forest stakeholders – Action Plan developed

- Establishment of mechanisms to foster stakeholder involvement in the forestry sector – Action Plan developed

- Development of an effective organizational structure – Action Plan developed

- Development of a Forest Management System with Stakeholder Involvement – Action Plan PARTIALLY developed; need to complete

- Develop strategies to improve earning or revenue potential – Action Plan developed

- Development of an efficient and responsive forestry information system – Action Plan developed

- Development of an effective national forest public awareness program – Action Plan NOT yet developed

- Design and implement capacity building program for the needs of the organization – Action Plan NOT yet developed

- Development of a comprehensive enforcement plan – Action Plan NOT yet developed

- Two additional strategic directions were proposed but not “adopted” by the group:

- Monitor the importation of forest products

- Keep all strategies in present plan

Action Planning for a New Forest Plan

Working in small groups, FD Staff used the findings of Worksheet 2, and the Strategic Directions agreed on to build Action Plans for the FD for the next five years (Worksheet 3, please see Appendix 4).  The Action Plans developed were for six (6) Strategic Directions, and are listed below from Table 7 - 12:

- Establishment of an effective incentive program to cover the various needs of forest stakeholders (Table 7)

- Establishment of mechanisms to foster stakeholder involvement in the forestry sector (Table 8)

- Development of an effective organizational structure (Table 9)

- Development of a Forest Management System with Stakeholder Involvement (Table 10)

- Develop strategies to improve earning or revenue potential (Table 11)

- Development of an efficient and responsive forestry information system (Table 12)

Table 7 	Effective Incentive Program

| Strategic Direction | Establishment of an effective incentive program to cover the various needs of forest stakeholders |  |
| --- | --- | --- |
| Objective To encourage investment in forest development and conservation |  |  |
| Key Activities/Targets 1. Free seedlings, and at cost for some species - private land owners - Remission of property tax for certain planted lands – private land owners - Duty concession and GCT waiver on capital goods – private land owners - Long-term conditional leasing of public lands for forest based activities: private land owners; NGOs; service groups - Free technical advice – rural and urban – all - Grants from NFMC Fund for forest-based activities – all - Public recognition for good forest management practices – model and agro-foresters - Public advertising of timber sales – all - Identify and promote opportunities for private land owners to benefit from international programs (e.g. carbon sequestration). Geographical Areas of Emphasis Nationwide |  | Roles and Responsibilities NGOs/CBOs; Private Sector; Central Government Agency: FD. MOF, NEPA MOF, FD FD, MOF FD, NLA, MOF FD ##### FD, private sector FD, NEPA, MOA FD FD, MLE Team Members P. Virgo Susie Latham John Latham |

Table 8		LFMCs

| Strategic Direction | Establishment of mechanisms to foster stakeholder involvement in the forestry sector |  |
| --- | --- | --- |
| Objective To organize LFMCs that involve all stakeholders in watersheds |  |  |
| Key Activities/Targets - Identify stakeholders (public, private, individuals) - Share information - Organize and attend meetings, contacts (formal, informal) - Mobilize communities/agencies - Seek collaboration with agencies - School outreach programs - Plan, coordinate meetings (preliminary) - Seek formal endorsement - Discussion of objectives, functions, structure, procedural arrangements (constitution) - Formalize group launch operational Geographical Areas of Emphasis Communities close to forested areas and in the watershed |  | Roles and Responsibilities: NGOs/CBOs; Private Sector; Central Government Agency: National Environment and Planning Agency, Ministry of Health, Ministry of Land and Environment, Social Development Commission, Ministry of Agriculture. CBOs: provide membership NGOs: technical support (logistics) - Capacity building reports) Private sector: funding and technical expertise Central government agencies: logistics, technical support - administrative assistance Interested individuals: membership - technical support - information dissemination Team Members Y. Reid M. Hinds N. Bennett |

Table 9		Effective Organizational Structure

| Strategic Direction | Development of an effective organizational structure |  |
| --- | --- | --- |
| Objective To enhance performance and productivity of the Forestry Department |  |  |
| Key Activities/Targets - Identify goals and objectives of organization - Identify needs - Create suitable organizational structure to accomplish goals; by identifying units and positions - Determine reporting relationships - Examine/review present job descriptions to see if they meet needs - Interview staff - Rewrite old and prepare new job descriptions to realign job functions - Design and implement an objective performance management systems - Set realistic targets - Sensitize staff to changes - Develop effective incentives program for staff - Develop succession plan, linked to training plan Geographical Areas of Emphasis All Regions and Head Office |  | Roles and Responsibilities: NGOs/CBOs; Private Sector; Central Government Agency: - Ministry of Finance - Office of the Services Commissions - Cabinet Office - Ministry of Agriculture - Private Consultants - MIND (Training of staff) - Director HRM & Ad. (FD) - Conservator - Senior Personnel Officer (FD) - Unit and Regional Heads - Staff (FD) Team Members M. Headley M. Stephenson B. Watt-Stewart |

Table 10	Forest Management System

| Strategic Direction | Development of a Forest Management System with Stakeholder Involvement |  |
| --- | --- | --- |
| Objective To identify and map forest resources of Jamaica and determine their natural development and sustainable use to generate goods and services for the benefit of stakeholders |  |  |
| Key Activities/Targets LFMCs Prepare LFMPs that contain the following information: - An assessment of resources - Determine commercial component - Schedule harvesting - Monitor harvesting - Replacement of resources Note: The key activities and targets for this strategy need to be expanded. Geographical Areas of Emphasis |  | Roles and Responsibilities: NGOs/CBOs; Private Sector; Central Government Agency: FD FD FD ##### FD Team Members K. Porter M. Barrett L. Nelson |

Table 11	Strategies to Improve Revenue Potential

| Strategic Direction | Develop strategies to improve earning or revenue potential |  |
| --- | --- | --- |
| Objective Identify and implement income-generating opportunities. |  |  |
| Key Activities/Targets - Establish viable and attractive eco-tourism/recreational areas (cabins, cave exploration, hiking, picnics, weddings, camping, etc.) - Permits and licensing systems - Timber and forest produce sales - Seedling sales (identify most lucrative species) - Technical services (assessments, surveying, reforestation packages) - Certification - Packaging and sale of seeds - Information (GIS maps, manuals) - Training for public on forestry - Leases - Carbon sequestration Geographical Areas of Emphasis Head Office Cockpit Country Gourie Clydesdale Moneague Internet Sales - Global |  | Roles and Responsibilities: NGOs/CBOs; Private Sector; Central Government Agency: - TPDCO, JTB – promotion; TNC – marketing; NLA, UDC - FD; private sector; Accountant General - FD; private sector - FD; Private nurseries - FD; WRA, NEPA, Mines & Geology - Bureau of Standard; FD; JMA, PSOJ - Private landowners - FD, MLE, Land database (National). - FD; Public - NLA; FD Team Members Donna Lowe Dorothy Hansel Rainee Oliphant |

Table 12	Forestry Information System

| Strategic Direction | Development of an efficient and responsive forestry information system |  |
| --- | --- | --- |
| Objective To provide accurate and timely information to meet both internal and external demand. |  |  |
| Key Activities/Targets - Develop a documentation and records management centre - Collect, collate and disseminate forestry related information - Establish an effective communication network - Development of an information manual - Conduct forest resource evaluation for sustainable forest management Geographical Areas of Emphasis Island wide |  | Roles and Responsibilities: NGOs/CBOs; Private Sector; Central Government Agency: - MOA - MLE - NLA - International journals & reports - UWI - IOJ - FD - Private sector Team Members Owen Evelyn Alli Morgan Stephanie Donaldson |

Another three (3) Strategic Directions were identified as:

- Development of an effective national forest public awareness programme (Table 13)

- Design and implement capacity building programme for the needs of the organization (Table 14)

- Development of a comprehensive enforcement plan (Table 15)

Action Plans were not completed for these at the Retreat, but the Workshop participant’s preliminary comments on these Strategic Directions are as shown in Tables 13 to 15.

Table 13	National Forest Public Education Program

| Strategic Direction | Development of an effective national forest public awareness program |  |
| --- | --- | --- |
| Action Plan not developed |  |  |
| Key Activities/Targets - Develop adult-friendly education programs - Increase public awareness centres (devote resources to urban forestry) - Enhance FD’s visibility in national media Geographical Areas of Emphasis |  | Roles and Responsibilities: NGOs/CBOs; Private Sector; Central Government Agency: Team Members |

Table 14	Capacity Building Program

| Strategic Direction | Design and implement capacity building program for the needs of the organization |  |
| --- | --- | --- |
| Action Plan not developed |  |  |
| Key Activities/Targets - Design and administer training programs to meet FD needs - Establish incentives for increasing staff morale - Increase FD capacity to satisfy needs of commercial end users - Develop a training plan to capture internal and external needs - Provide appropriate training for staff members - Develop and maintain a motivating climate to build morale both internal and external - Develop a continual and consistent capacity building program Geographical Areas of Emphasis |  | Roles and Responsibilities: NGOs/CBOs; Private Sector; Central Government Agency: Team Members |

Table 15	Comprehensive Enforcement Plan

| Strategic Direction | Development of a comprehensive enforcement plan |  |
| --- | --- | --- |
| Action Plan not developed |  |  |
| Key Activities/Targets - Implement an effective enforcement plan - Prepare updated Forest Act and Regulations Geographical Areas of Emphasis |  | Roles and Responsibilities: NGOs/CBOs; Private Sector; Central Government Agency: Team Members |

## Victory Circle

Participants developed a “vision” for what the Forest Plan would look like in the year 2006. The visions or victories are listed below in Diagram 1:

DIAGRAM 1 – VICTORY CIRCLE

###### Final draft of FP completed and 	Major studies indicated in ‘old’ plan

###### approved by the Minister 		completed

###### of Agriculture

Adequate funding for technical	FD adequately staffed, funded and organized to

field programs			implement the completed plan

Comprehensive NFMCP printed	A new E.A. which focuses on the development

and ready for use			of the forestry sector

Tighter internal linkages		A re-structured and reorganized FD with

qualified and committed staff

Organizational structures that can 	All regional offices fully equipped with

support FD’s new mandate		inter connected computer system

A cadre of dedicated and committed	Agreement on the new FD organizational

staff assigned and working with	structure

stakeholders in LFMCs

Adequate levels of funding secured

(GOJ, external)

Schedule or Calendar for Preparation of 2006-2010 National Forest Management and Conservation Plan

Participants then developed a Calendar of Activities for preparation of the 2006 -2010 National Forest Management and Conservation Plan. The Calendar of Activities included:

- Four Work Areas with Teams and Team Leaders, namely:

  - Drafting of Plans – Stephanie Donaldson

  - Research and Information – Rainee Oliphant

  - Community Consultation – Noel Bennett

  - Financial Resource Requirement – Dorothy Hansel

- Launch or First Activity for each Team;

- Activities over six quarters (November-December 04 to January – March 06); and

- A Victory Complete or what each work area would look like when the activity is completed

The Calendar of Activities is listed on Page 21 (Diagram 3) of this Report

## Project Steering Committee (PSC)

A Project Steering Committee was selected to implement this Calendar of Activities, namely:

- Chairperson	-	Conservator

- Team 1		-	Stephanie

- Team 2		-	Rainee

- Team 3		-	Noel

- Team 4		-	Dorothy

Other members would include:

- NEPA

- Representative from LFMCs

- MLE

- NLA

- WRA

- RADA

## Implementation Wedge

An Implementation Wedge, listing the immediate activities that must take place was developed, and is listed below as Diagram 2:

Diagram 2	Immediate Plan of Action

1st week of December

Develop Budget

2nd week of December

Meeting of work teams

End of November

Document Workshops complete

2nd week of December

Present to staff

2nd week of January

Project Steering Committee

1st week of December

FD Management meeting

2nd week of December

Invitation to external agencies

Diagram 3	Schedule or Calendar for Preparation of 2006-2010 National Forest Management and Conservation Plan

| Working Areas | ## Work Teams | Launch Activity | Q1 Nov – Dec 04 | Q2 Jan – March 05 | Q3 April – June 05 | Q4 July – Sept 05 | Q5 Oct – Dec 05 | Q6 Jan – March 06 | Victory Complete |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Drafting of Plans | Stephanie Donaldson Marilyn Headley Keith Porter Maxine Hinds Susie Latham | Finalize report of the ‘retreat’ and prepare an “outline for the planning process” (of 2006 FP) | Begin preparing “Outline” and Budget (e.g. initial meeting with other agencies) “Proceedings” prepared | Meeting(s) (all SCM) to review 2001 Forest Plan Finalize “outline” Begin drafting of 2006 Plan | First draft of 2006 F.P. by June 1, 2005 to SCM for review | Incorporate comments for 2nd draft by July 30, 2005 Circulate 2nd draft to SCM August/05 2nd draft for public comments by Sep/05 | Incorporate public comments for 3rd draft by mid Nov/05 Circulate 3rd draft to SCM by mid Nov/05 | Receive SCM comments January 20, 2006 Final FP to Minister by February 15, 2006 Printed Plan ready by March 15, 2006 | 2006 Forest Plan printed. |
| Research & Information | Rainee Oliphant Donna Lowe Lawrence Nelson Owen Evelyn | Review NFMCP 2001 and draft plan of action | Assign different parts of NFMCP 2001 to each member for review - achievements - shortfalls - keepers Prepare budget | Review similar forest plans (non FD) Generate information on assigned sections | Circulate draft information reports for comments Compile feedback | Incorporate feedback into 2nd draft information report Circulate 2nd draft for final comments | Meet to finalize team draft information report Present final report to the drafting team | Relax on the beach | Old plan reviewed Updated Information included in new NFMCP. |
| # Community Consultation | Noel Bennett Patrick Virgo Beverly Watt-Stewart Margaret Stephenson | Organize a series of staff meeting: - Head Office - Regional | Prepare bulletin and budget | Meet Central Region staff Meet Head Office and Eastern Region staff Meet with Western Region staff. | Organize workshop with representatives of government agencies Arrange meeting with private sector representatives Meeting with international agencies Organize workshop with NGO’s and Universities | Community consultation Kingston Metropolitan area Community consultation – Central Community consultation Western (1st session) Community consultation – Eastern Community consultation Western (2nd session) Community consultation - Youth | Arrange review of draft Forest Plan Arrange (reverse) feedback (draft) | Work with Team 1 to coordinate official launch/presentation of Plan | All stakeholders consulted Inputs documented and incorporated in Plan |
| Financial Resource Requirements | Dorothy Hansel York Reid John Latham Alli Morgan Michael Barrett, | Request budget from other working groups | Obtain budgets Review budgets | Identify potential funding sources Obtain commitments from funding sources Approach funding sources to requests funds Obtain funds and distribute. | Continue approaching funding sources Obtain funds and distribute | Obtain funds and distribute | Obtain funds and distribute | Obtain funds and distribute | Adequate resources obtained to allows completion of the Plans. |

APPENDIX 1

AGENDA

Forestry Department Retreat

The Sans Souci Resort & Spa, Ocho Rios, November 3-5, 2004

Purpose

The Retreat will involve the Senior Management Staff of the Forestry Department in:

- Receiving presentation/s on the existing status of the National Forest Management and Conservation Plan, taking into consideration the FD new role as a Executive Agency;

- Developing a Balance Sheet that will assist the FD to determine the things that it did well in implementing the National Forest Management and Conservation Plan, and those that could be improved on;

- Establishing the Strategic Directions for the FD for a new National Forest Management and Conservation Plan;

- Establishing an Action Plan for the FD over the next Five Years; and

- Establishing timeline for next steps (preparation of draft plan, public consultations to present draft document, printing etc)

Day 1 – Wednesday, November 3, 2004

3:00 – 3:30 pm		Arrivals

3:30 – 4:15 pm	Preliminaries (Prayer, Welcome, Introductions, Expectations, and Significance of the Retreat)

4:15 – 5:30 pm 		Presentation and Discussions

Day 2 – Thursday, November 4, 2004

9:00 – 10:30 am 	Session 1 - Preparation and Reflection on a Balance Sheet –

Worksheet 1

10:30 – 11:00 am	BREAK

11:00 am – 12:30 pm	Session 2 - Identification and Prioritization of Issues

– Worksheet 2

12:30 – 1:30 pm	LUNCH

1:30 – 3:30 pm		Session 3 – Strategic Directions Workshop - Brainstorming

3:30 – 4:00 pm		BREAK

4:00 – 5:30 pm		Session 4 – Action Planning – Worksheet 3

Day 3 – Friday, November 5, 2004

9:00 – 10:30 am	Session 5 – Action Planning – Calendar of Events

10:30 – 11:00 am	BREAK

11:00 am – 12:30 pm	Session 6 – Reports and Next Steps

12:30 – 1:30 pm	LUNCH

1:30 – 2:30 pm		Session 7 – Wrap-up and Closing of Retreat

APPENDIX 2

Worksheet 1- Balance Sheet

| DONE WELL | COMMENTS |
| --- | --- |
| NEED IMPROVEMENT/NOT DONE | COMMENTS |

APPENDIX 3

Worksheet 2 – Issues For Discussion

- Policy and Legal Framework

- 2001 Updated Forest Policy; Watershed Policy; Other Related Policies’ including Mining Policy, National Land Policy, Policies related to Local Governance and all Environmental Policies

- Forest Policy Issues: Governance; Investors; Stakeholder Participation

- Forest Act and Regulations (including the preparation of TOR to review the Forest Act in 2005)

- Protection Status and Ownership – NLA handing over of Crown lands to FD

- Forest Protection – Patrolling Plan

- Role of  Executive Agency

- Forest Resources Information

- Forest Cover and land Use Classification Systems

- Definitions of Land Use and Forest Cover Types (harmonize national)

- Past Forestry Research

- Direction of Present Forestry Research (as it relates to the future role of FD)

- Collaboration in Research (dissemination of information)

- Local Forest Management Plans

- Fuel-wood, Charcoal and Yam-stick Production

- Minor Forest Products

- Role of  Executive Agency

- Role of FD in Forestry Productive Sector

- Private Sector Involvement

- Production of Seedlings

- Replanting and harvesting – who is responsible?

- Lumber Supply and Demand

- Lumber Quality

- Sustainable Development of Wood-based Industries

- Role of  Executive Agency

- Community Participation and Public Education

- Co-management of Forest Reserves and Crown Lands, including Mangrove Areas

- Local Forestry Management Committees

- The Role of FD in Community Forestry, and Community Activities

- Role of  Executive Agency

- Communications Program

- Local and National

- Administration and HRD

- Context/Role of Executive Agency

- Access to Information

- Succession Leadership

- Procurement of Resources

- Training

- Accounting

- Information/Documentation (files, library etc.)

Feedback on Issues

1.	List the three (3) major lessons and/or practices that should be carried forward from the existing Forest Plan to the new one for the area you are examining

- _____________________________________________________________________

_____________________________________________________________________

_____________________________________________________________________

- _____________________________________________________________________

_____________________________________________________________________

_____________________________________________________________________

- _____________________________________________________________________

_____________________________________________________________________

_____________________________________________________________________

- Name the three (3) key new issues you believe must be included in a new Forest Plan for the area you are examining

- _____________________________________________________________________

_____________________________________________________________________

_____________________________________________________________________

- _____________________________________________________________________

_____________________________________________________________________

_____________________________________________________________________

- _____________________________________________________________________

_____________________________________________________________________

_____________________________________________________________________

- Name the three (3) key Organizations and their likely role you believe is necessary to partner the FD in the successful implementation of this new plan

- _____________________________________________________________________

_____________________________________________________________________

_____________________________________________________________________

- _____________________________________________________________________

_____________________________________________________________________

_____________________________________________________________________

- _____________________________________________________________________

_____________________________________________________________________

_____________________________________________________________________

- List any other comments you have regarding this area in the Forest Plan

APPENDIX 4

Worksheet 3 – Action Planning

Action Planning for a New Forest Plan

| Strategic Direction No. |  |  |
| --- | --- | --- |
| Objective |  |  |
| Key Activities/Targets Geographical Areas of Emphasis |  | Roles and Responsibilities: NGOs/CBOs; Private Sector; Central Government Agency: Team Members |

APPENDIX 5

List of Participants

# Retreat Participants:  FD - List of Senior Managers

- Marilyn Headley	Conservator

- Rainee Oliphant	Legal Officer

- Maxine Hinds	Public Awareness

- Beverly Watt-Stewart	Senior Personnel Officer

- Margaret Stephenson	Director, Human Resources Management and Administration

- Dorothy Hansel	Director of Finance

- Donna Lowe	Nursery Co-ordinator

- Stephanie Donaldson	Public Awareness/Public Relations

- Keith Porter	Director, Technical Services

- Michael Barrett	Regional Officer – Western

- York Reid	Regional Officer – Central

- Patrick Virgo	Regional Officer – Eastern

- Owen Evelyn 	National Project Manager, Trees for Tomorrow Project

- Alli Morgan	Resource Management & Planning Officer

- Lawrence Nelson	Senior Research Officer

- Noel Bennett	Rural Sociologist

- Susie Latham	Project Manager, Trees for Tomorrow Project

- John Latham	Agro-economist, Trees for Tomorrow Project

- Trevor Spence	Facilitator